## Untitled
Project_ID | Project_Name | Product_Line | Requesting_Country | Lead_Team | Project_Type | Priority | Start_Date | Planned_End | Status | Planned_Hours | Actual_Hours | Pct_Complete | Lead_Engineer | Hours_Variance_Pct | Overrun_Flag
EP-101 | Straw chopper housing tooling - production engineering | Combine Harvester | USA | Production Engineering | Production Engineering | High | 2025-04-17 | 2025-06-07 | On Hold | 430 | 246 | 55 | Simran Gill | 0.0402 | OK
EP-102 | Straw chopper housing manuals - technical documentation | Combine Harvester | Germany | Technical Documentation | Technical Documentation | Medium | 2025-06-05 | 2025-07-22 | Completed | 350 | 332 | 100 | Preeti Saini | -0.0514 | OK
EP-103 | Feeder housing tooling - production engineering | Combine Harvester | USA | Production Engineering | Production Engineering | Medium | 2025-06-15 | 2025-08-25 | Completed | 930 | 883 | 100 | Lalit Verma | -0.0505 | OK
EP-104 | Front axle bracket - concept | Tractor | USA | Machine Design | Concept | Medium | 2025-07-21 | 2025-11-17 | Completed | 850 | 810 | 100 | Pooja Arora | -0.0471 | OK
EP-105 | Bale chamber hydraulics tooling - production engineering | Baler | France | Production Engineering | Production Engineering | Medium | 2025-09-05 | 2025-10-27 | Completed | 480 | 479 | 100 | Balbir Randhawa | -0.0021 | OK
EP-106 | Cooling package - concept | Combine Harvester | USA | Simulation (FEA/CFD) | Concept | Low | 2025-09-14 | 2025-12-22 | Completed | 880 | 881 | 100 | Tarun Mehra | 0.0011 | OK
EP-107 | Transmission housing manuals - technical documentation | Tractor | France | Technical Documentation | Technical Documentation | High | 2025-10-08 | 2025-12-20 | Completed | 270 | 242 | 100 | Ishita Bajaj | -0.1037 | OK
EP-108 | Operator display and controls - cost reduction | Combine Harvester | USA | Electrical & Electronics | Cost Reduction | High | 2025-10-27 | 2026-02-12 | Completed | 440 | 502 | 100 | Shweta Kapoor | 0.1409 | Overrun
EP-109 | Rear linkage - detail design | Tractor | USA | Machine Design | Detail Design | High | 2025-10-29 | 2026-03-20 | Completed | 1600 | 1695 | 100 | Neha Rawat | 0.0594 | OK
EP-110 | Cab and operator station tooling - production engineering | Combine Harvester | Germany | Production Engineering | Production Engineering | Medium | 2025-11-10 | 2026-01-24 | Completed | 850 | 838 | 100 | Balbir Randhawa | -0.0141 | OK
EP-111 | Steering hydraulics manuals - technical documentation | Tractor | Germany | Technical Documentation | Technical Documentation | Medium | 2025-12-09 | 2026-01-15 | Completed | 510 | 434 | 100 | Yogesh Kataria | -0.149 | OK
EP-112 | Sensor harness - validation support | Forage Harvester | Germany | Electrical & Electronics | Validation Support | Medium | 2025-12-29 | 2026-02-19 | Completed | 550 | 670 | 100 | Rohit Dogra | 0.2182 | Overrun
EP-113 | Knotter drive manuals - technical documentation | Baler | France | Technical Documentation | Technical Documentation | High | 2026-01-05 | 2026-03-13 | Completed | 500 | 415 | 100 | Preeti Saini | -0.17 | OK
EP-114 | Chopping drum guard - detail design | Forage Harvester | USA | Machine Design | Detail Design | Medium | 2026-01-22 | 2026-06-16 | Completed | 3030 | 2918 | 100 | Gurdeep Sethi | -0.037 | OK
EP-115 | Engine bay cooling - concept | Forage Harvester | USA | Simulation (FEA/CFD) | Concept | Medium | 2026-01-28 | 2026-04-18 | Completed | 1420 | 1542 | 100 | Divya Nair | 0.0859 | OK
EP-116 | Main wiring harness - cost reduction | Combine Harvester | Germany | Electrical & Electronics | Cost Reduction | Medium | 2026-01-28 | 2026-05-27 | Completed | 1170 | 1308 | 100 | Anjali Sood | 0.1179 | Overrun
EP-117 | Main wiring harness - concept | Combine Harvester | USA | Electrical & Electronics | Concept | Medium | 2026-02-10 | 2026-06-07 | Completed | 630 | 707 | 100 | Shweta Kapoor | 0.1222 | Overrun
EP-118 | Cleaning shoe and sieve box - validation support | Combine Harvester | Germany | Simulation (FEA/CFD) | Validation Support | Low | 2026-02-17 | 2026-03-20 | Completed | 520 | 539 | 100 | Divya Nair | 0.0365 | OK
EP-119 | Cab ECU mounting - detail design | Tractor | Germany | Electrical & Electronics | Detail Design | Medium | 2026-02-21 | 2026-07-02 | Completed | 1620 | 1700 | 100 | Shweta Kapoor | 0.0494 | OK
EP-120 | Pickup tine assembly tooling - production engineering | Baler | Germany | Production Engineering | Production Engineering | Medium | 2026-03-06 | 2026-06-06 | Completed | 380 | 376 | 100 | Simran Gill | -0.0105 | OK
EP-121 | Chassis frame manuals - technical documentation | Combine Harvester | France | Technical Documentation | Technical Documentation | Medium | 2026-03-12 | 2026-05-25 | Completed | 600 | 543 | 100 | Preeti Saini | -0.095 | OK
EP-122 | Feeder housing - concept | Combine Harvester | USA | Machine Design | Concept | Medium | 2026-03-20 | 2026-06-07 | Completed | 1490 | 1574 | 100 | Sandeep Malik | 0.0564 | OK
EP-123 | Cooling package manuals - technical documentation | Combine Harvester | Germany | Technical Documentation | Technical Documentation | Medium | 2026-03-30 | 2026-06-07 | Completed | 340 | 300 | 100 | Ishita Bajaj | -0.1176 | OK
EP-124 | Main wiring harness - validation support | Combine Harvester | Germany | Electrical & Electronics | Validation Support | High | 2026-03-30 | 2026-05-30 | Completed | 490 | 613 | 100 | Rohit Dogra | 0.251 | Overrun
EP-125 | Engine bay cooling - concept | Forage Harvester | Germany | Simulation (FEA/CFD) | Concept | Medium | 2026-04-07 | 2026-06-17 | Completed | 870 | 866 | 100 | Arvind Khurana | -0.0046 | OK
EP-126 | Cleaning shoe and sieve box - detail design | Combine Harvester | Germany | Simulation (FEA/CFD) | Detail Design | Medium | 2026-04-22 | 2026-09-02 | Completed | 2390 | 2520 | 100 | Tarun Mehra | 0.0544 | OK
EP-127 | Cab and operator station tooling - production engineering | Combine Harvester | Germany | Production Engineering | Production Engineering | Medium | 2026-04-24 | 2026-07-15 | Completed | 940 | 843 | 100 | Balbir Randhawa | -0.1032 | OK
EP-128 | Cleaning shoe and sieve box - detail design | Combine Harvester | Germany | Simulation (FEA/CFD) | Detail Design | Medium | 2026-04-26 | 2026-08-28 | Completed | 1950 | 2139 | 100 | Tarun Mehra | 0.0969 | OK
EP-129 | Cleaning shoe and sieve box - validation support | Combine Harvester | France | Simulation (FEA/CFD) | Validation Support | Medium | 2026-05-03 | 2026-07-15 | Completed | 710 | 722 | 100 | Divya Nair | 0.0169 | OK
EP-130 | Knotter drive - cost reduction | Baler | Germany | Machine Design | Cost Reduction | Medium | 2026-05-06 | 2026-07-23 | Completed | 740 | 790 | 100 | Pooja Arora | 0.0676 | OK
EP-131 | Knotter drive tooling - production engineering | Baler | Germany | Production Engineering | Production Engineering | Medium | 2026-05-09 | 2026-07-27 | Completed | 520 | 491 | 100 | Balbir Randhawa | -0.0558 | OK
EP-132 | Cab and operator station - validation support | Combine Harvester | Germany | Machine Design | Validation Support | Medium | 2026-05-10 | 2026-08-06 | Completed | 680 | 654 | 100 | Gurdeep Sethi | -0.0382 | OK
EP-133 | Pickup tine assembly manuals - technical documentation | Baler | Germany | Technical Documentation | Technical Documentation | Medium | 2026-05-23 | 2026-07-22 | Completed | 350 | 339 | 100 | Ishita Bajaj | -0.0314 | OK
EP-134 | Rear linkage - concept | Tractor | USA | Machine Design | Concept | Low | 2026-05-27 | 2026-08-10 | Completed | 760 | 699 | 100 | Sandeep Malik | -0.0803 | OK
EP-135 | Chassis frame - detail design | Combine Harvester | France | Simulation (FEA/CFD) | Detail Design | Medium | 2026-06-06 | 2026-09-11 | Completed | 2540 | 2445 | 100 | Tarun Mehra | -0.0374 | OK
EP-136 | Grain tank unloading auger - cost reduction | Combine Harvester | Germany | Machine Design | Cost Reduction | Low | 2026-06-10 | 2026-10-02 | Completed | 550 | 565 | 100 | Neha Rawat | 0.0273 | OK
EP-137 | Engine bay cooling - cost reduction | Forage Harvester | Germany | Simulation (FEA/CFD) | Cost Reduction | Medium | 2026-06-12 | 2026-08-14 | Completed | 1120 | 1276 | 100 | Divya Nair | 0.1393 | Overrun
EP-138 | Wiring and sensors - validation support | Baler | France | Electrical & Electronics | Validation Support | Medium | 2026-06-22 | 2026-09-10 | Completed | 840 | 1035 | 100 | Karan Walia | 0.2321 | Overrun
EP-139 | Feeder housing - concept | Combine Harvester | Germany | Machine Design | Concept | High | 2026-06-25 | 2026-10-15 | On Hold | 1240 | 458 | 40 | Anil Chauhan | -0.0766 | OK
EP-140 | Engine bay cooling - detail design | Forage Harvester | USA | Simulation (FEA/CFD) | Detail Design | Medium | 2026-06-29 | 2026-10-29 | On Hold | 2590 | 2582 | 95 | Divya Nair | 0.0494 | OK
EP-141 | Knotter drive - validation support | Baler | USA | Machine Design | Validation Support | Medium | 2026-07-03 | 2026-08-30 | Completed | 450 | 424 | 100 | Pooja Arora | -0.0578 | OK
EP-142 | Feeder housing - concept | Combine Harvester | Germany | Machine Design | Concept | Medium | 2026-07-12 | 2026-09-15 | On Hold | 1250 | 663 | 55 | Neha Rawat | -0.0356 | OK
EP-143 | Main wiring harness - concept | Combine Harvester | USA | Electrical & Electronics | Concept | Medium | 2026-07-15 | 2026-11-09 | In Progress | 1410 | 1193 | 80 | Anjali Sood | 0.0576 | OK
EP-144 | Rear linkage - concept | Tractor | Germany | Machine Design | Concept | High | 2026-07-16 | 2026-11-11 | In Progress | 1490 | 1028 | 70 | Ritu Bhandari | -0.0144 | OK
EP-145 | Cooling package - validation support | Combine Harvester | Germany | Simulation (FEA/CFD) | Validation Support | Medium | 2026-07-18 | 2026-09-26 | Completed | 590 | 623 | 100 | Arvind Khurana | 0.0559 | OK
EP-146 | Feeder housing tooling - production engineering | Combine Harvester | Germany | Production Engineering | Production Engineering | Medium | 2026-07-20 | 2026-09-18 | Completed | 660 | 596 | 100 | Simran Gill | -0.097 | OK
EP-147 | Rear linkage - cost reduction | Tractor | USA | Machine Design | Cost Reduction | High | 2026-07-20 | 2026-10-07 | Completed | 940 | 867 | 100 | Neha Rawat | -0.0777 | OK
EP-148 | Spout hydraulics manuals - technical documentation | Forage Harvester | USA | Technical Documentation | Technical Documentation | Low | 2026-07-20 | 2026-09-27 | Completed | 290 | 274 | 100 | Preeti Saini | -0.0552 | OK
EP-149 | Steering hydraulics - concept | Tractor | Germany | Hydraulics | Concept | Low | 2026-07-22 | 2026-09-23 | Completed | 1150 | 1249 | 100 | Harpreet Bedi | 0.0861 | OK
EP-150 | Straw chopper housing - validation support | Combine Harvester | Germany | Machine Design | Validation Support | Medium | 2026-08-01 | 2026-09-14 | Completed | 780 | 750 | 100 | Gurdeep Sethi | -0.0385 | OK
EP-151 | Main wiring harness - validation support | Combine Harvester | Germany | Electrical & Electronics | Validation Support | Medium | 2026-08-05 | 2026-10-08 | Completed | 320 | 351 | 100 | Rohit Dogra | 0.0969 | OK
EP-152 | Cab and operator station - concept | Combine Harvester | USA | Machine Design | Concept | Low | 2026-08-08 | 2026-10-18 | In Progress | 590 | 435 | 75 | Gurdeep Sethi | -0.0169 | OK
EP-153 | Bale chamber hydraulics - cost reduction | Baler | Germany | Hydraulics | Cost Reduction | Medium | 2026-08-22 | 2026-12-16 | In Progress | 500 | 294 | 45 | Vikas Tandon | 0.3067 | Overrun
EP-154 | Cab ECU mounting - validation support | Tractor | USA | Electrical & Electronics | Validation Support | Low | 2026-08-24 | 2026-10-15 | Completed | 430 | 532 | 100 | Karan Walia | 0.2372 | Overrun
EP-155 | Main wiring harness - validation support | Combine Harvester | USA | Electrical & Electronics | Validation Support | Low | 2026-08-24 | 2026-09-24 | Completed | 800 | 881 | 100 | Karan Walia | 0.1013 | Overrun
EP-156 | Spout hydraulics - validation support | Forage Harvester | Germany | Hydraulics | Validation Support | High | 2026-08-25 | 2026-10-11 | Completed | 620 | 815 | 100 | Vikas Tandon | 0.3145 | Overrun
EP-157 | Main wiring harness - concept | Combine Harvester | Germany | Electrical & Electronics | Concept | Medium | 2026-09-16 | 2026-11-15 | In Progress | 1140 | 772 | 55 | Rohit Dogra | 0.2313 | Overrun
EP-158 | Steering hydraulics manuals - technical documentation | Tractor | USA | Technical Documentation | Technical Documentation | Medium | 2026-09-18 | 2026-11-16 | In Progress | 270 | 137 | 60 | Preeti Saini | -0.1543 | OK
EP-159 | Engine bay cooling - concept | Forage Harvester | France | Simulation (FEA/CFD) | Concept | Medium | 2026-09-20 | 2026-12-04 | On Hold | 1090 | 377 | 35 | Arvind Khurana | -0.0118 | OK
EP-160 | Feed roll assembly - cost reduction | Forage Harvester | Germany | Machine Design | Cost Reduction | Low | 2026-09-22 | 2027-01-09 | In Progress | 630 | 161 | 25 | Pooja Arora | 0.0222 | OK